## Slide 1
IMPLEMENTATION PLAN
Local Agentic Document
Extraction System
Pure VLM + Multi-Agent Architecture for Healthcare RCM
MODEL
Qwen3-VL 8B
BACKEND
LM Studio
AGENTS
4 Specialized
COMPLIANCE
HIPAA Ready

## Slide 2
Executive Summary
THE CHALLENGE
Healthcare RCM requires 97%+ accuracy on sensitive documents while maintaining HIPAA compliance and data sovereignty.
OUR SOLUTION
Streamlined 4-agent system using local VLM with 3-layer anti-hallucination and schema-driven extraction.
4
Focused Agents
3
Validation Layers
100%
Local Processing
12
Week Timeline
WHY 4 AGENTS INSTEAD OF 9?
50% fewer VLM calls
2x faster processing
Simpler orchestration
Easier maintenance
DESIGN IMPROVEMENTS
Old: 6-8 VLM calls/page
New: 3-4 VLM calls/page
Old: 45-60 sec/page
New: 15-25 sec/page
Old: 6 validation layers
New: 3 effective layers

## Slide 3
4-Agent Architecture
📄
PDF Input
→
PREPROCESSOR
PDF → Images
Quality Check
No VLM calls
→
AGENT 1: ORCHESTRATOR
LangGraph State Machine • Workflow Control • Error Handling
0 VLM calls
AGENT 2: ANALYZER
Document classification
Structure detection
Page relationships
1 VLM call/doc
AGENT 3: EXTRACTOR
Schema-driven extraction
Dual-pass verification
Confidence scoring
2 VLM calls/page
AGENT 4: VALIDATOR
Schema validation
Hallucination detection
Cross-page merging
0-1 VLM call/doc
→
✓
JSON
Output
VLM BACKEND: Qwen3-VL 8B via LM Studio
Local GPU • OpenAI-Compatible API • 32K Context
~6GB
VRAM (INT4)
3-4
VLM calls/page

## Slide 4
PHASE 0 • WEEK 1
Prerequisites and Environment Setup
STEP-BY-STEP TASKS
1
Procure Hardware
RTX 4090 (24GB) or A6000 • 32-64GB RAM • 500GB NVMe
2
Install LM Studio
Download from lmstudio.ai • Enable vision support
3
Download Qwen3-VL Model
Q4_K_M quantization (~6GB VRAM) • All layers to GPU
4
Configure Local Server
Port 1234 • Context 8192-32768 • Enable image inputs
5
Setup Python Environment
Python 3.11 • venv • Install dependencies
6
Verify Vision Capability
Test with sample image • Confirm structured output
REQUIREMENTS
VRAM Options
FP16
18GB
INT8
10GB
INT4
6GB
Python Packages
langgraph
PyMuPDF
openai
pydantic
Pillow
MILESTONE
VLM responds correctly to image + text prompt via localhost:1234

## Slide 5
PHASE 1 • WEEKS 2-3
Core Infrastructure
WEEK 2: PDF Processing Pipeline
1
Build PDF ingestion module
2
Implement page extraction (300 DPI)
3
Add quality enhancement filters
4
Create batch processing manager
5
Write unit tests for pipeline
WEEK 2: LM Studio Client
1
Create connection manager class
2
Build vision request handler
3
Implement response parser
4
Add retry logic with tenacity
5
Add health check monitoring
WEEK 3: Schema System
1
Define base schema structure
2
Create field type validators
3
Build CMS-1500 schema
4
Build EOB/Remittance schema
5
Add cross-field rule engine
PRE-BUILT HEALTHCARE RCM SCHEMAS
Medical Claim
CMS-1500 / UB-04 • ICD-10 • CPT codes
EOB / Remittance
Payments • Adjustments • Reason codes
Lab Report
Results • Reference ranges • Flags
PDF processor
LM client
Schema library
Unit tests
DELIVERABLES

## Slide 6
PHASE 2 • WEEKS 4-6
4-Agent Framework Development
WEEK 4: ORCHESTRATOR
1. Setup LangGraph project
2. Define state machine states
3. Build transition logic
4. Implement checkpointing
5. Add error handling
6. Create retry policies
0 VLM calls
WEEK 4-5: ANALYZER
1. Create agent base class
2. Build classification prompt
3. Implement structure detector
4. Add page relationship logic
5. Build schema selector
6. Test with sample docs
1 VLM call/doc
WEEK 5: EXTRACTOR
1. Build extraction prompt
2. Implement dual-pass logic
3. Add field comparison
4. Create confidence scorer
5. Add visual grounding
6. Handle table extraction
2 VLM calls/page
WEEK 6: VALIDATOR
1. Build schema validator
2. Add pattern detection
3. Implement cross-field rules
4. Build cross-page merger
5. Add confidence calibration
6. Create output formatter
0-1 VLM call/doc
AGENT DESIGN PRINCIPLES
1
Single Responsibility
2
Stateless Operations
3
Confidence Scoring
4
Graceful Degradation
LANGGRAPH STATE MACHINE
INIT → ANALYZE → EXTRACT → VALIDATE → COMPLETE/REVIEW
5
States
4
Agents
3-4
VLM/page

## Slide 7
PHASE 3 • WEEKS 7-8
3-Layer Anti-Hallucination System
1
Prompt Engineering
Built into all agent prompts
Grounding instructions
Do not guess rules
Return null if unsure
Structured output format
Owner: All Agents
2
Dual-Pass Extraction
Implemented in Extractor Agent
Two extraction passes
Different prompt variations
Field-by-field comparison
Mismatch flagging
Owner: Extractor Agent
3
Pattern + Rule Validation
Implemented in Validator Agent
Repetitive value detection
Cross-field consistency
Code validation (NPI, ICD)
Math and date logic checks
Owner: Validator Agent
CONFIDENCE SCORE ACTIONS
0.95+
Auto-Accept
0.85-0.94
Accept + Note
0.70-0.84
Verify
0.50-0.69
Re-Extract
Below 0.50
Human Review
HUMAN-IN-THE-LOOP
Auto-flagging, review interface, correction feedback loop
Target: Less than 10% Review Rate

## Slide 8
PHASES 4-5 • WEEKS 9-12
Integration, Testing and Deployment
PHASE 4: INTEGRATION (Weeks 9-10)
Week 9: REST API Development
1. Setup FastAPI project structure
2. Create POST /extract endpoint
3. Add GET /tasks/{id} status
4. Implement batch processing
5. Add async task queue
Week 10: Testing Suite
1. Unit tests for each agent
2. Integration tests (end-to-end)
3. Accuracy tests (golden dataset)
4. Hallucination adversarial tests
5. Performance benchmarks
POST /api/v1/extract
GET /api/v1/tasks/{id}
POST /api/v1/batch
GET /api/v1/health
PHASE 5: DEPLOYMENT (Weeks 11-12)
Week 11: HIPAA Compliance
1. Verify 100% local processing
2. Implement AES-256 encryption
3. Setup role-based access control
4. Enable comprehensive audit logs
5. Configure secure temp cleanup
Week 12: Production Launch
1. Setup monitoring dashboards
2. Configure alerting rules
3. Write operations runbook
4. Train operations team
5. Go-live with pilot documents
Capacity
Single GPU: 50-100 pg/hr • Multi-GPU: 200-400 pg/hr

## Slide 9
12-Week Implementation Timeline
0
Week 1
Setup
1
Weeks 2-3
Core
2
Weeks 4-6
4 Agents
3
Weeks 7-8
Validation
4
Weeks 9-10
Testing
5
Weeks 11-12
Deploy
Phase
Duration
Key Deliverables
Phase 0
Week 1
Hardware, LM Studio, model download, Python env
Phase 1
Weeks 2-3
PDF pipeline, LM client, schema system, RCM schemas
Phase 2
Weeks 4-6
4 agents (Orchestrator, Analyzer, Extractor, Validator), LangGraph
Phase 3
Weeks 7-8
3-layer anti-hallucination, human-in-the-loop, confidence tuning
Phase 4
Weeks 9-10
REST API, batch processing, unit/integration/accuracy tests
Phase 5
Weeks 11-12
HIPAA compliance, monitoring, alerting, documentation, go-live
Buffer: 2-week contingency for edge cases and model tuning
Total: 12-14 weeks

## Slide 10
Success Criteria and Next Steps
PERFORMANCE TARGETS
FIELD ACCURACY
95%+
HALLUCINATION RATE
2% or less
PROCESSING SPEED
15-25s/pg
99.5%
Uptime
10%
Review Rate
3-4
VLM/page
NEXT STEPS
1
Procure hardware (RTX 4090)
2
Collect sample corpus (100+ docs)
3
Define custom schemas
4
Assign dev team (2-3 engineers)
KEY RISKS
Hallucinations: 3-layer verification
Doc quality: Enhancement pipeline
HIPAA: 100% local processing
Ready to Begin Phase 0